## Progress Planning and Tracking
Project Name: | whatsthe.buzz
Report Date: | 2017-03-07
[5 empty] | Milestone #1 |  |  |  | Milestone #2 |  |  |  | Milestone #3
Deliverable | Tasks | Complete% | Current Status Memo | Assigned To | 2017-01-23 | 01/30 | 02/06 | 02/13 | 02/20 | 02/27 | 03/06 | 03/13 | 03/20 | 03/27 | 04/03 | 04/10 | 04/17 | 04/24
Database Update | Multi-survey fix | 25% | Started | Jonathan, Patrick | Milestone #1 02/06: 2; Milestone #1 02/13: 2
Patrick | Dynamic survey questions | 100% | Done | Jonathan | bar: Milestone #1 02/06 to Milestone #1 02/13
Ben | Multi-reports for admins | 0% |  | Ben | Milestone #2 03/06: 2; Milestone #2 03/13: 2; Milestone #3 03/20: 3; Milestone #3 03/27: 3; Milestone #3 04/03: 3; Milestone #3 04/10: 4
Jonathan |  | 0%
Website Implementation | Implement password recovery | 0% |  |  | Milestone #2 03/06: 1; Milestone #2 03/13: 2; Milestone #3 03/20: 5; Milestone #3 03/27: 6; Milestone #3 04/03: 4; Milestone #3 04/10: 5
Sherri | Implement dynamic questions | 100% | Done | Sherri, Neisha | Milestone #1 01/30: 4; Milestone #1 02/06: 4; Milestone #1 02/13: 2; Milestone #2 02/20: 2; Milestone #2 02/27: 2
Neisha | Implement multi-survey | 75% |  | Jonathan, Patrick | Milestone #1 02/13: 1; Milestone #2 02/20: 5; Milestone #2 02/27: 4; Milestone #2 03/06: 4; Milestone #2 03/13: 3
Jonathan |  | 0%
Password Recovery | Forgot password link - website | 0% |  |  | Milestone #2 03/06: 2; Milestone #2 03/13: 3; Milestone #3 03/20: 3; Milestone #3 03/27: 4; Milestone #3 04/03: 2; Milestone #3 04/10: 3
-possibly | Add recovery module - website/database | 0% |  |  | Milestone #2 03/06: 3; Milestone #2 03/13: 2; Milestone #3 03/20: 2; Milestone #3 03/27: 2; Milestone #3 04/03: 2; Milestone #3 04/10: 2
| Use email as auth for reset/recovery - database | 0% |  |  | Milestone #2 03/06: 1; Milestone #2 03/13: 1; Milestone #3 03/20: 2; Milestone #3 03/27: 4; Milestone #3 04/03: 3; Milestone #3 04/10: 2
0%
Documentation | User test results | 0% | Work in Progress | Sherri, Ben | Milestone #2 02/20: 2; Milestone #2 02/27: 1; Milestone #2 03/06: 2; Milestone #2 03/13: 2
Neisha | Design documents | 15% | Work in Progress | Neisha |  | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2
| Dynamic question list | 100% | Done | Ben, Patrick | bar: Milestone #1 01/30
| M1 Powerpoint | 100% | Done | Everyone | Milestone #1 02/13: 2
| M2 Powerpoint | 10% |  | Neisha, Sherri | Milestone #2 03/13: 2
| M3 Powerpoint | 0% |  | Neisha, Sherri
| C-Day Presentation Materials | 0% |  | Everyone | Milestone #3 04/17: 2
Sherri | Github Repository setup | 100% | Done | Sherri | bar: Milestone #2 03/06
| AWS Virtual Server creation & setup | 0% | Work in Progress | Sherri | Milestone #2 03/13: 2; Milestone #3 04/03: 2; Milestone #3 04/17: 1
| Project website | 100% | Done | Sherri | Milestone #1 02/06: 4; Milestone #1 02/13: 1; Milestone #2 02/27: 1; Milestone #2 03/13: 2; Milestone #3 03/27: 1; Milestone #3 04/10: 2; Milestone #3 04/17: 1; Milestone #3 04/24: 1
User Testing | User testing survey design | 90% | Subject to change | Neisha | bar: Milestone #1 01/30; Milestone #1 02/13; Milestone #2 03/06; Milestone #3 04/03
| 20 interviews/tests | 0% | Work in Progress | Ben, Patrick | Milestone #2 03/06: 2; Milestone #2 03/13: 2; Milestone #3 03/20: 3; Milestone #3 03/27: 1; Milestone #3 04/03: 2; Milestone #3 04/10: 2
0%
| Total workload | 186 |  |  | 0 | 7 | 13 | 11 | 10 | 9 | 20 | 24 | 19 | 22 | 20 | 21 | 7 | 3
Legend |  |  | Due M1 - 2/17
Planned | 2 |  | Due M2 - 3/17
Delayed | 1 |  | Due M3 - 4/14
Number | Workload: man hour